## Sheet1
| 81 Unique Datasets (multiple unique worksheets within some datasets) | No. Records | No. of Fields | Actual Time Taken (hrs) | Time per Field (minutes) | Hours To Complete | Working Days To complete | Weeks to Complete | $ Budget
· IOT1804:
o 18-04 IOT BOT data.xlsx |  | 3559 | 44 | 8.75 | 11.9318 | Estimate based on completed work to date |  |  |  | 2019-01-04 17:22
o 18-04 IOT BOT GPS data.kml
o 18-04 IOT PATH geolocation data – all.kml
o IOT Apr 2018 LHalling ento samples.xlsx |  | 325 | 35 | 3.5 | 6 | 247.05 | 32.94 | 6.588 | 21740.4 | (average doesn't include the first dataset)
o IOT April 2018 PPath data All Collectors.xlsx |  | 307 | 184 | 3.75 | 1.2228
o IOT Ento JO April 2018.xlsx |  | 648 | 70 | 3 | 2.5714
· IOT1809:
o IOT Botany Data September 2018.xlsx |  | 518 | 40 | 1.75 | 2.625
o IOT September 2018 Ento Data.xlsx |  | 954 | 56 | 3.25 | 3.4821
o IOT September 2018 Host Data KStralow.xlsx
o IOT September 2018 Pathology Data HVala.xlsx
· PNG15JPHS:
o 20150721 2015 PNG survey NAQS data - ENTO v1.0.xls
o 20150901 2015 PNG survey NAQS data - BOT v1.0.xlsx
o 20151013 2015 PNG survey data NAQS data - PATH v1.0.xlsx
· PNG16JPHS:
o 16-04 PNG BOT data.xlsx
o Ento Data PNG Sandaun Province April 2016.xlsx
o PNG April 2016 patho data.xlsm
· PNG17BorderIntercept:
o Data_Botany_HK.xlsx
o intercept survey data with more plant pathol and botany to be added.xlsm
o PNG OSS Survey 2017 - MG feb18.xlsx
· PNG17Madang:
o ESepik_BotanyObservations_2017.xlsx
o ESepik_BotanySpecimens_2017_DBtemplateStyle.xlsx
o plant pathology negative data1.xlsm
o plant pathology1.xlsm
o PNG Nov_2017_Ento_NS_Survey data Final_29_10_18.xlsx
o PNG_Entomology_extraction_ SAC cleaned data.xlsx
· PNG17Treaty:
o Bot PNGTreaty Village Ptracker Data March 2017 - cleaned and updated August 2017.xls
o Entomology Treaty Villages Full Data.xlsx
o PPath PNG March 2017 Treaty Village Data - FINAL.xlsx
· PNG18Bougainville:
o 18-09 PNG botany GPS data.kml
o 18-09 PNG Bougainville botany data.xlsx
o 2018_09_P_PNG_AROB_ppath_IPHSP.xlsx
o 2018-09_Bougainville_PNG_Entomology_DRB.xlsx
· PNG2018Treaty:
o 1802_PlantPath_PNG Treaty Village Survey 2018 - Current.xlsx
o Botany_2018 PNG Eastern Treaty Village Data - Draft1.xlsx
o ENTO Negative Data PNG Treaty Village 17-18.xlsx
o PNG Treaty Village 17-18 ENTO.xlsx
· SLB15JPHS:
o 20150910 2015 Solomons survey NAQS data - BOT v1.0.xlsx
o 20151008 Solomon Islands 2015 Survey Data - ENTO v1.0.xlsx
o 20151008 Solomon Islands 2015 Survey Data_PATH v1.0.xlsx
· SLB16JPHS:
o 16-09 Solomon Islands BOT data.xlsx
o Ento Solomon Sep2016 – edited.xlsx
o Ento Solomon Sep2016 - including duplicates.xlsx
o SI_PlantPath_2016-negative.xlsx
o SI_PlantPath_2016-sampless.xlsx
· SLB17JPHS:
o 17-04 Solomon Islands BOT data.xlsx
o Solomon 2017 Ento data- duplicates removed.xlsx
o Solomon pathology collections 2017.xlsx
o Solomon pathology negative data 2017.xlsx
· SLB18CSCocoa:
o Solomon plant path 11 18 negative data.xlsx
o Solomon plant path 11 18.xlsx
· SLB18CSCoconut:
o NAQS_Entomology__Solomons_April_ 2018.xlsx
o Solomon April 2018 plant pathology collections.xlsm
o Solomon April 2018 plant pathology negative data.xlsm
o Solomons Botany 2018-04 - Preliminary data 2018_05_02.xlsx
· SLBPre2015JPHS:
o SI Feb 2012 locality.xlsx
· Bob Macfarlane Insects of the Solomon Islands list.xlsx
· TLS15JPHS:
o 20150615 2015 Timor-Leste survey NAQS DNQB data - BOTANY v1.0.xlsx
o 20150615 2015 Timor-Leste survey NAQS DNQB data - PATHOLOGY (4 worksheets) v1.0.xlsx
o 20150625 2015 Timor-Leste survey NAQS DNQB data - ENTO (2 worksheets) v1.2.xlsx
· TLS16JPHS:
o 20160412 2016 Timor-Leste survey Murray Sharman data PATHOLOGY_v1.xlsx
o 20160418 2016 Timor-Leste survey NAQS DNQB data BOTANY_v1.xlsx
o 20160418 2016 Timor-Leste survey NAQS DNQB data PATHOLOGY_v2.xlsx
o 20160506 2016 Timor-Leste survey NAQS DNQB data ENTOMOLOGY_v1 (2).xlsx
· TLS17HSFebMar:
o Ento TL Mar2017_final draft.xlsx
o IPHSP_BotanyDATA-Specimens+observations_TimorLeste2017.xlsx
o Negative Data Pathology cleaned up.xlsx
o TL317PPspecimens.xlsx
· TLS17HSSep:
o 17-09 Timor Leste BOT data v1.xlsx
o 17-09 Timor Leste ENTO data v3.xlsx
o TL_PPath_Sept2017_AllCollectors.xlsx
· TLS17PathWork:
o DNA samples from Timor workshop
· TLS18BorderIntercept:
o Botany Data Timor Leste June 2018.xlsx
o Entomology Data Timor-Leste (June2018).csv
o Quarantena Interceptions (2018).xlsx
o TimoreLeste2018BorderInterceptPathology.csv
· TLS18BorderRegion:
o 1804 Timor Leste Plant Health Survey_PPath_IPHSP.xlsx
o BotanyData_IPHSP_April2018.xlsx
o ENTO Negative Data Timor Leste 17-18.xlsx
o ENTO Timor Leste Specimen data 17-18.xlsx
· TLS18Thrips:
o Timor-Leste Thrips Survey (August 2018) - All parties.xlsx
· Copy of Disease list TL2016 draft.xlsx
insect list from NAQS surveys Genus level.xlsx

## New Calculations
| 81 Unique Datasets (multiple unique worksheets within some datasets) | No. Records | No. of Fields | Actual Time Taken (hrs) | Time per Field (minutes) | Hours To Complete | Working Days To complete | Weeks to Complete | $ Budget
· IOT1804:
o 18-04 IOT BOT data.xlsx |  | 3559 | 44 | 8.75 | 11.9318 | Estimate based on completed work to date |  |  |  | 2019-01-04 17:22
o 18-04 IOT BOT GPS data.kml |  | 163 | 16 | 1 | 3.75
o 18-04 IOT PATH geolocation data – all.kml |  | 13 | 15 | 1 | 4
o IOT Apr 2018 LHalling ento samples.xlsx |  | 325 | 45 | 3.5 | 4.6667 | 195.75 | 26.1 | 5.22 | 17226
o IOT April 2018 PPath data All Collectors.xlsx |  | 80 | 46 | 4.75 | 6.1957
o IOT Ento JO April 2018.xlsx |  | 648 | 37 | 3 | 4.8649
· IOT1809:
o IOT Botany Data September 2018.xlsx |  | 518 | 40 | 1.75 | 2.625
o IOT September 2018 Ento Data.xlsx |  | 954 | 25 | 3.25 | 7.8
o IOT September 2018 Host Data KStralow.xlsx |  | 792 | 38 | 1 | 1.5789
o IOT September 2018 Pathology Data HVala.xlsx |  | 364 | 45 | 1.25 | 1.6667
· PNG15JPHS:
o 20150721 2015 PNG survey NAQS data - ENTO v1.0.xls |  | 237 | 36 | 1.75 | 2.9167
o 20150901 2015 PNG survey NAQS data - BOT v1.0.xlsx |  | 760 | 38 | 1.25 | 1.9737
o 20151013 2015 PNG survey data NAQS data - PATH v1.0.xlsx |  | 101 | 36 | 2.25 | 3.75
· PNG16JPHS:
o 16-04 PNG BOT data.xlsx |  | 56 | 38 | 1.25 | 1.9737
o Ento Data PNG Sandaun Province April 2016.xlsx |  | 111 | 33 | 2 | 3.6364
o PNG April 2016 patho data.xlsm |  | 86 | 35 | 1 | 1.7143
· PNG17BorderIntercept:
o Data_Botany_HK.xlsx |  | 135 | 33 | 2.25 | 4.0909
o intercept survey data with more plant pathol and botany to be added.xlsm |  | 44 | 43 | 2.5 | 3.4884
o PNG OSS Survey 2017 - MG feb18.xlsx
· PNG17Madang:
o ESepik_BotanyObservations_2017.xlsx
o ESepik_BotanySpecimens_2017_DBtemplateStyle.xlsx
o plant pathology negative data1.xlsm
o plant pathology1.xlsm
o PNG Nov_2017_Ento_NS_Survey data Final_29_10_18.xlsx
o PNG_Entomology_extraction_ SAC cleaned data.xlsx
· PNG17Treaty:
o Bot PNGTreaty Village Ptracker Data March 2017 - cleaned and updated August 2017.xls
o Entomology Treaty Villages Full Data.xlsx
o PPath PNG March 2017 Treaty Village Data - FINAL.xlsx
· PNG18Bougainville:
o 18-09 PNG botany GPS data.kml
o 18-09 PNG Bougainville botany data.xlsx
o 2018_09_P_PNG_AROB_ppath_IPHSP.xlsx
o 2018-09_Bougainville_PNG_Entomology_DRB.xlsx
· PNG2018Treaty:
o 1802_PlantPath_PNG Treaty Village Survey 2018 - Current.xlsx
o Botany_2018 PNG Eastern Treaty Village Data - Draft1.xlsx
o ENTO Negative Data PNG Treaty Village 17-18.xlsx
o PNG Treaty Village 17-18 ENTO.xlsx
· SLB15JPHS:
o 20150910 2015 Solomons survey NAQS data - BOT v1.0.xlsx
o 20151008 Solomon Islands 2015 Survey Data - ENTO v1.0.xlsx
o 20151008 Solomon Islands 2015 Survey Data_PATH v1.0.xlsx
· SLB16JPHS:
o 16-09 Solomon Islands BOT data.xlsx
o Ento Solomon Sep2016 – edited.xlsx
o Ento Solomon Sep2016 - including duplicates.xlsx
o SI_PlantPath_2016-negative.xlsx
o SI_PlantPath_2016-sampless.xlsx
· SLB17JPHS:
o 17-04 Solomon Islands BOT data.xlsx
o Solomon 2017 Ento data- duplicates removed.xlsx
o Solomon pathology collections 2017.xlsx
o Solomon pathology negative data 2017.xlsx
· SLB18CSCocoa:
o Solomon plant path 11 18 negative data.xlsx
o Solomon plant path 11 18.xlsx
· SLB18CSCoconut:
o NAQS_Entomology__Solomons_April_ 2018.xlsx
o Solomon April 2018 plant pathology collections.xlsm
o Solomon April 2018 plant pathology negative data.xlsm
o Solomons Botany 2018-04 - Preliminary data 2018_05_02.xlsx
· SLBPre2015JPHS:
o SI Feb 2012 locality.xlsx
· Bob Macfarlane Insects of the Solomon Islands list.xlsx
· TLS15JPHS:
o 20150615 2015 Timor-Leste survey NAQS DNQB data - BOTANY v1.0.xlsx
o 20150615 2015 Timor-Leste survey NAQS DNQB data - PATHOLOGY (4 worksheets) v1.0.xlsx
o 20150625 2015 Timor-Leste survey NAQS DNQB data - ENTO (2 worksheets) v1.2.xlsx
· TLS16JPHS:
o 20160412 2016 Timor-Leste survey Murray Sharman data PATHOLOGY_v1.xlsx
o 20160418 2016 Timor-Leste survey NAQS DNQB data BOTANY_v1.xlsx
o 20160418 2016 Timor-Leste survey NAQS DNQB data PATHOLOGY_v2.xlsx
o 20160506 2016 Timor-Leste survey NAQS DNQB data ENTOMOLOGY_v1 (2).xlsx
· TLS17HSFebMar:
o Ento TL Mar2017_final draft.xlsx
o IPHSP_BotanyDATA-Specimens+observations_TimorLeste2017.xlsx
o Negative Data Pathology cleaned up.xlsx
o TL317PPspecimens.xlsx
· TLS17HSSep:
o 17-09 Timor Leste BOT data v1.xlsx
o 17-09 Timor Leste ENTO data v3.xlsx
o TL_PPath_Sept2017_AllCollectors.xlsx
· TLS17PathWork:
o DNA samples from Timor workshop
· TLS18BorderIntercept:
o Botany Data Timor Leste June 2018.xlsx
o Entomology Data Timor-Leste (June2018).csv
o Quarantena Interceptions (2018).xlsx
o TimoreLeste2018BorderInterceptPathology.csv
· TLS18BorderRegion:
o 1804 Timor Leste Plant Health Survey_PPath_IPHSP.xlsx
o BotanyData_IPHSP_April2018.xlsx
o ENTO Negative Data Timor Leste 17-18.xlsx
o ENTO Timor Leste Specimen data 17-18.xlsx
· TLS18Thrips:
o Timor-Leste Thrips Survey (August 2018) - All parties.xlsx
· Copy of Disease list TL2016 draft.xlsx
insect list from NAQS surveys Genus level.xlsx

## Sheet2
Stage | Estimated Hours To Complete | Days To complete | Weeks to Complete | $ Budget
2019-01-04 17:22
Estimate based on completed work to date as at:
Review | 195.75 | 26.1 | 5.22 | 17226
Cleanse | 84.6818 | 11.2909 | 2.2582 | 7452
Total | 280.4318 | 37.3909 | 7.4782 | 24678
Completeness (2mins to clean/record) | 198.2333 | 26.4311 | 5.2862 | 17444.5333 |  | is equal to numbe rof incomplete records * 2 minutes to inspect and amended per record?
number of incomplete records | 1878 |  | 1.6693 | 5508.8
datasets cleansed | 24
total datasets | 76
estimated total incomplete records |  |  | 5947
total unique records |  |  | 10279
incomplete records |  |  | 4177
incomplete records likely complete |  |  | 2299
% datasets cleansed | 31.58%

## Extension times
Project Extension No. | Project Description | Estimated Hours To Complete | Days To complete | Weeks to Complete | $ Budget
1 | Map data fields to SIMS | 37.5 | 5 | 1 | 3300
2 | Review datasets pre-2015 | 150 | 20 | 4 | 13200
3 | Codify/Standardise Terminologies | 75 | 10 | 2 | 6600
4 | Assign BiotaID to Pest/Host Taxonomy field | 37.5 | 5 | 1 | 3300
5 | Finish review of unalaysed datasets | 75 | 10 | 2 | 6600
6 |  |  | 0 | 0 | 0
Total | 0 | 75 | 10 | 2 | 33000