## Sheet1
| 81 Unique Datasets (multiple unique worksheets within some datasets) | Final No. Records | Incomplete Host Genus | Incomplete Host Species | Incomplete Pest Genus | Incomplete Pest Species | No. of Fields | Actual Time Taken (hrs) | Time per Field (minutes) | Hours To Complete | Working Days To complete | Weeks to Complete | $ Budget
· IOT1804:
o 18-04 IOT BOT data.xlsx |  | 3529 | 0 | 235 | 0 | 10 | 46 | 5 | 6.5217 | Estimate based on completed work to date |  |  |  | 2019-01-10 13:34
o 18-04 IOT BOT GPS data.kml
o 18-04 IOT PATH geolocation data – all.kml
o IOT Apr 2018 LHalling ento samples.xlsx |  | 197 | 12 | 133 | 3 | 19 | 45 | 2 | 2.6667 | 85.2188 | 11.3625 | 2.2725 | 7499.25
o IOT April 2018 PPath data All Collectors.xlsx |  | 87 | 1 | 1 | 87 | 87 | 108 | 1.5 | 0.83333
o IOT Ento JO April 2018.xlsx |  | 515 | 13 | 180 | 13 | 13 | 94 | 1.75 | 1.117
· IOT1809:
o IOT Botany Data September 2018.xlsx |  | 377 | 0 | 0 | 0 | 9 | 49 | 1.25 | 1.5306
o IOT September 2018 Ento Data.xlsx |  | 851 | 5 | 502 | 34 | 48 | 28 | 0.75 | 1.6071
o IOT September 2018 Host Data KStralow.xlsx |  | 792 | 30 | 151 | 792 | 792 | 39 | 0.75 | 1.1538
o IOT September 2018 Pathology Data HVala.xlsx |  | 364 | 0 | 0 | 364 | 364 | 48 | 0.75 | 0.9375
· PNG15JPHS:
o 20150721 2015 PNG survey NAQS data - ENTO v1.0.xls |  | 237 | 6 | 6 | 88 | 118 | 43 | 0.5 | 0.69767
o 20150901 2015 PNG survey NAQS data - BOT v1.0.xlsx |  | 760 | 760 | 760 | 0 | 0 | 45 | 0.75 | 1
o 20151013 2015 PNG survey data NAQS data - PATH v1.0.xlsx |  | 101 | 0 | 1 | 101 | 101 | 44 | 0.75 | 1.0227
· PNG16JPHS:
o 16-04 PNG BOT data.xlsx |  | 56 | 34 | 40 | 22 | 22 | 45 | 0.5 | 0.66667
o Ento Data PNG Sandaun Province April 2016.xlsx |  | 111 | 6 | 19 | 26 | 43 | 40 | 0.5 | 0.75
o PNG April 2016 patho data.xlsm |  | 86 | 0 | 0 | 86 | 86 | 39 | 1 | 1.5385
· PNG17BorderIntercept:
o Data_Botany_HK.xlsx |  | 135 | 31 | 31 | 18 | 18 | 43 | 1 | 1.3953
o intercept survey data with more plant pathol and botany to be added.xlsm |  | 44 | 2 | 7 | 43 | 44 | 54 | 0.5 | 0.55556
o PNG OSS Survey 2017 - MG feb18.xlsx |  | 130 | 0 | 2 | 22 | 25 | 40 | 0.5 | 0.75
· PNG17Madang:
o ESepik_BotanyObservations_2017.xlsx |  | 1251 | 0 | 0 | 0 | 0 | 23 | 0.5 | 1.3043
o plant pathology negative data1.xlsm |  | 65 | 1 | 1 | 65 | 65 | 48 | 0.75 | 0.9375
o PNG_Entomology_extraction_ SAC cleaned data.xlsx |  | 150 | 13 | 67 | 30 | 54 | 37 | 0.5 | 0.81081
· PNG17Treaty:
o Bot PNGTreaty Village Ptracker Data March 2017 - cleaned and updated August 2017.xls |  | 311 | 0 | 0 | 0 | 1 | 41 | 0.75 | 1.0976
o Entomology Treaty Villages Full Data.xlsx |  | 130 | 26 | 84 | 26 | 38 | 36 | 0.75 | 1.25
o PPath PNG March 2017 Treaty Village Data - FINAL.xlsx |  | 145 | 31 | 31 | 145 | 145 | 44 | 1.25 | 1.7045
· PNG18Bougainville:
o 18-09 PNG botany GPS data.kml
o 18-09 PNG Bougainville botany data.xlsx |  | 3432 | 0 | 216 | 0 | 173 | 46 | 1 | 1.3043
o 2018_09_P_PNG_AROB_ppath_IPHSP.xlsx
o 2018-09_Bougainville_PNG_Entomology_DRB.xlsx
· PNG2018Treaty:
o 1802_PlantPath_PNG Treaty Village Survey 2018 - Current.xlsx
o Botany_2018 PNG Eastern Treaty Village Data - Draft1.xlsx
o ENTO Negative Data PNG Treaty Village 17-18.xlsx
o PNG Treaty Village 17-18 ENTO.xlsx
· SLB15JPHS:
o 20150910 2015 Solomons survey NAQS data - BOT v1.0.xlsx
o 20151008 Solomon Islands 2015 Survey Data - ENTO v1.0.xlsx
o 20151008 Solomon Islands 2015 Survey Data_PATH v1.0.xlsx
· SLB16JPHS:
o 16-09 Solomon Islands BOT data.xlsx
o Ento Solomon Sep2016 – edited.xlsx
o Ento Solomon Sep2016 - including duplicates.xlsx
o SI_PlantPath_2016-negative.xlsx
o SI_PlantPath_2016-sampless.xlsx
· SLB17JPHS:
o 17-04 Solomon Islands BOT data.xlsx
o Solomon 2017 Ento data- duplicates removed.xlsx
o Solomon pathology collections 2017.xlsx
o Solomon pathology negative data 2017.xlsx
· SLB18CSCocoa:
o Solomon plant path 11 18 negative data.xlsx
o Solomon plant path 11 18.xlsx
· SLB18CSCoconut:
o NAQS_Entomology__Solomons_April_ 2018.xlsx
o Solomon April 2018 plant pathology collections.xlsm
o Solomon April 2018 plant pathology negative data.xlsm
o Solomons Botany 2018-04 - Preliminary data 2018_05_02.xlsx
· SLBPre2015JPHS:
o SI Feb 2012 locality.xlsx
· Bob Macfarlane Insects of the Solomon Islands list.xlsx
· TLS15JPHS:
o 20150615 2015 Timor-Leste survey NAQS DNQB data - BOTANY v1.0.xlsx
o 20150615 2015 Timor-Leste survey NAQS DNQB data - PATHOLOGY (4 worksheets) v1.0.xlsx
o 20150625 2015 Timor-Leste survey NAQS DNQB data - ENTO (2 worksheets) v1.2.xlsx
· TLS16JPHS:
o 20160412 2016 Timor-Leste survey Murray Sharman data PATHOLOGY_v1.xlsx
o 20160418 2016 Timor-Leste survey NAQS DNQB data BOTANY_v1.xlsx
o 20160418 2016 Timor-Leste survey NAQS DNQB data PATHOLOGY_v2.xlsx
o 20160506 2016 Timor-Leste survey NAQS DNQB data ENTOMOLOGY_v1 (2).xlsx
· TLS17HSFebMar:
o Ento TL Mar2017_final draft.xlsx
o IPHSP_BotanyDATA-Specimens+observations_TimorLeste2017.xlsx
o Negative Data Pathology cleaned up.xlsx
o TL317PPspecimens.xlsx
· TLS17HSSep:
o 17-09 Timor Leste BOT data v1.xlsx
o 17-09 Timor Leste ENTO data v3.xlsx
o TL_PPath_Sept2017_AllCollectors.xlsx
· TLS17PathWork:
o DNA samples from Timor workshop
· TLS18BorderIntercept:
o Botany Data Timor Leste June 2018.xlsx
o Entomology Data Timor-Leste (June2018).csv
o Quarantena Interceptions (2018).xlsx
o TimoreLeste2018BorderInterceptPathology.csv
· TLS18BorderRegion:
o 1804 Timor Leste Plant Health Survey_PPath_IPHSP.xlsx
o BotanyData_IPHSP_April2018.xlsx
o ENTO Negative Data Timor Leste 17-18.xlsx
o ENTO Timor Leste Specimen data 17-18.xlsx
· TLS18Thrips:
o Timor-Leste Thrips Survey (August 2018) - All parties.xlsx
· Copy of Disease list TL2016 draft.xlsx
insect list from NAQS surveys Genus level.xlsx